## Bug Report
Bug ID | Bug Title | Module | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment | Screenshot Ref | Reported By | Date Reported | Comments
BUG-001 | Password fields not cleared after duplicate email error on Register page | User Registration | 1. Go to Register page 2. Fill all fields with valid data 3. Enter an email that is already registered 4. Click Continue 5. Observe the form after the error message appears | After the duplicate email warning is shown, Password and Confirm Password fields should be cleared for security reasons. | Password and Confirm Password fields retain the previously entered values after the error message 'E-Mail Address is already registered!' is displayed. | Major | High | Open | Chrome (latest) / Windows 11 https://opencart.abstracta.us | BUG-001-screenshot.png | Nimisha Pathak | 09 June 2026 | Security concern — password should not persist on validation error
BUG-002 | Cart page main heading incorrectly displays 'Use Gift Certificate (0.00kg)' | Shopping Cart | 1. Add any product to cart 2. Click Shopping Cart in header 3. Observe the main page heading (H1) | The main heading of the Shopping Cart page should display 'Shopping Cart' or 'Your Cart'. | The main H1 heading on the Shopping Cart page incorrectly displays 'Use Gift Certificate (0.00kg)' instead of the expected cart page title. | Minor | Medium | Open | Chrome (latest) / Windows 11 https://opencart.abstracta.us | BUG-002-screenshot.png | Nimisha Pathak | 09 June 2026 | UI defect — wrong section title used as page heading

## Summary
Severity | Total | Open | Fixed | Closed | Rejected
Critical | 0 | 0 | 0 | 0 | 0
Major | 1 | 1 | 0 | 0 | 0
Minor | 1 | 1 | 0 | 0 | 0
Low | 0 | 0 | 0 | 0 | 0
TOTAL | 2 | 2 | 0 | 0 | 0